## Sheet1
Task | Start Date | Duration | Status
Planning | 2022-06-13 | 28 | Completed
UI Design | 2022-07-14 | 77 | In progress
Coding | 2022-07-28 | 72 | In progress
Testing | 2022-09-18 | 25 | Not Started
Deploy | 2022-10-14 | 9 | Not Started
Documentation | 2022-06-13 | 134 | In progress